## Slide 1
Volume Licensing
Proposal For
Scrum Implementation

## Slide 2
Agenda
Why To Go Agile?
Summary E2E Process
Roles & Responsibilities
Backlog Refinement
  Customer Promise
  Scenarios
  Deliverables
Sprint
  Definitions
Release Planning
  Release Cadence & Milestones
  Scope Tracking
  SOX Compliance

## Slide 3
Why To Go Agile?
Planning | 
As Is | Half yearly (Semester) planning twice in a year Post that, though new work is added, there is no further planning or prioritization meeting
To Be | A systematic process to prepare backlog (Customer promise, scenarios) Quarterly planning increment process to prioritize work for the next QR Quarterly planning (PI) and monthly backlog grooming ensures we can respond to changing business needs and deliver the highest business value
Release Cadence | 
As Is | Weekly releases are delivering values in shorter cycle. However it primarily targets bugs and simple scenarios Monthly releases are actually two month long (From scope lock to test complete, it spans across 8 weeks)
To Be | Continue with the weekly release cadence Monthly releases reduces to 6 weeks (4 weeks of dev sprint + 2 weeks of decoupled UAT) Fail fast, learn fast, deliver fast Quicker feedback from stakeholders Reduces code merge and deployment complexities In longer run, monthly releases shall be of 4 weeks from scope lock to UAT completion

## Slide 4
Why To Go Agile?
Efficiencies | 
As Is | Two parallel monthly releases increases work in progress, thus increases complexity Code management is complex across multiple release branches Multiple test environments need to be maintained Overlapping and repeated testing needs Team (PM, Dev, SE) needs to focus on multiple releases at time Each release gets prime attention few weeks before go live
To Be | Team to work on one release at a time Simplified code management One set of environments across releases Avoid overlapping testing needs due to one release at a time Lesser churn and deeper attention as team to focus on one release with smaller chunk of work
Release Churn | 
As Is | Multiple change requests increases scope churn
To Be | Scrum encourages to accept refined scope in a sprint resulting in lesser change requests Fixed capacity is associated with fixed scope as Sprint planning ensures capacity is mapped against granular estimates

## Slide 5
E2E Process Summary
Customer Promise Created
CP Assessed
CP Triaged
CP Added to POR
CP broken into scenarios
Scenarios are refined
Quarterly Planning Meeting
Scenarios are prioritized
Scenarios broken into deliverables
Deliverables written in detail
Sprint backlog refinement
Deliverables are ready for Sprint
Sprint planning
Deliverables broken into tasks
Sprint review
Sprint execution
Managing Customer
Promise
Managing Scenarios
Managing Deliverables
Managing
Sprint
Following is a depiction of Scrum process. It will be covered in detail in subsequent slides.
Indicates existing processes. However most of them do not have a formal structure around it. We shall streamline it as part of Scrum.
Each capability to present their backlog for next three months
At least one week before sprint starts
Formal meeting to finalize sprint scope
Review sprint outcome with the stakeholders

## Slide 6
Scrum Planning
Roles & Responsibilities

## Slide 7
Vertical Leads
As-is
To-be
Vertical Leads
Capability Lead
Program
Lead
Program
Lead
Capability Program Managers
Capability Product Owners
Capability Product Owner
Product
Owner
Product
Owner
Development Team 1
Development Team 2
Capability Development Team
Developers
Scrum Master
Developers
Developers
Scrum Master
Scrum - Roles
# of dev teams for each capability will be finalized by dev leads
Each dev team to have 5 to 7 members including Scrum Master
Experience PMs
Experience
Product Owners

## Slide 8
Existing Role | New Role | Major Responsibilities
Vertical Leads (Hari, Jill, Rob, Tom, Vic) | Vertical Leads | Customer promise management (Creation and approval) Drive half yearly planning exercise Participate in quarterly release planning to review priorities
Capability Lead PM (Sushma, Murali, Tushar, KK) | Capability Product Owner | Owner of the capability backlog Can own a CP or assign CP to a PO Create scenarios and deliverables for CP owned by him/her Prioritize capability backlog (scenarios) across CP based on organization priorities Represent capability in quarterly planning exercise Also works as a PO
Program Lead (ex. Capability PM - Vivek, Ashok, Ashwini); Experience PM ( (Janani, Naomi, Mike, Anand) | Product Owner / Experience Product Owner | Own a customer promise for assessment and execution Break CP into scenarios and deliverables Refine scenarios and deliverables (adding sufficient details for implementation) Work with CPO for prioritization Work with the dev team for implementation Experience PO will work across multiple capabilities PO / Dev leads for program execution
Roles – Mapped To Existing VL Roles

## Slide 9
Existing Role | New Role | Major Responsibilities
Dev Team (ex. Ordering dev team) | Dev Team(s) | Existing capability team to be transformed into multiple dev teams Work with PO for sprint backlog refinement Ownership to deliver the sprint objectives (design, develop, test and support)
Non-existent | Scrum Master | Facilitate the scrum team to accomplish sprint objectives Run daily scrum meeting Impediment removal Run sprint review and retrospection meeting, implement learnings for improvement Represent sprint team in weekly bedrock meeting
Dev Lead (ex. Mani, Bhupesh, Vaidya, Puneet) | Dev Lead | Help PO for customer promise assessment Focus on impediment management, team capability improvements, technical architectural direction
Roles – Mapped To Existing VL Roles

## Slide 10
Backlog Refinement
Customer Promise
Scenario
Deliverables

## Slide 11
Vertical Lead
Experience Product Owner / Product Owner
Creates a CP and assigns to PO
CP State = Proposed
*CP State = Pending Approval
* Indicates logical state for the CP; this will be implemented using State field and tags.
CP is discussed during triage meeting held once every 2 weeks
CP is approved for POR
and added to backlog
CP State = Committed
Customer Promise Backlog Refinement - 1
A vertical lead creates a customer promise, which may not be tied to a single capability
(While it may need work from multiple capabilities, the nature of the work is generic across capabilities – GDPR, Accessibility, Platform upgrades, Cloud migration or any other experience related work)
Consults SMEs,
Identifies impact across all capabilities,
completes CP assessment, and provides
high level estimates

## Slide 12
Vertical Lead
Capability
Product Owner
Product Owner
Creates a CP and assigns to CPO
Assigns CP to PO
Consults SMEs,
Identifies impact across all capabilities,
completes CP assessment, and provides
high level estimates
CP State = Proposed
*CP State = Pending Assessment
*CP State = Pending Approval
* Indicates logical state for the CP; this will be implemented using State field and tags.
CP is discussed during triage meeting held once every 2 weeks
CP is approved for POR
and added to backlog
CP State = Committed
Customer Promise Backlog Refinement - 2
A vertical lead creates a customer promise, which is specific to a capability
(While it may need work from multiple capabilities, it can be tied to a specific capability based on maximum impact)

## Slide 13
Scenario & Deliverable Backlog Refinement
Refine scenarios
Work with CPO to prioritize and add to approved backlog
Create scenarios
If work involves other capabilities, create a scenario and assign to CPO
Prioritized capability
backlog
Break a scenario into deliverable(s)
Detailed deliverables
Sprint backlog refinement
Work with dev team to ensure deliverable is ready for sprint planning
Capability PO (Capability A)
Dev Team
Experience PO /
PO (Capability A)
Capability PO (Capability B)
Write deliverables in detail including acceptance criteria
Following depicts how an approved customer promise will be broken into scenarios and deliverables for sprint execution
Refine scenarios
Detailed deliverables
Sprint backlog refinement
Deliverables ready for the sprint
Deliverables ready for the sprint

## Slide 14
Sprint Execution
Refined Backlog (Deliverables)
Sprint backlog (Deliverables)
Sprint Review
Sprint Retrospection
EPO/PO
Ops/Business
Dev Team
Including daily scrum meetings
Following depicts how dev team will work on deliverables as part of sprint execution
Sprint Planning
Break deliverables into tasks
Sprint Execution
EPO/PO joins to provide any clarifications
Ops/Business are invited on need basis
Next Sprint
CPO/Vertical Lead
CPO/Vertical leads are optional participants

## Slide 15
Ceremonies
Following example depicts timelines for different ceremonies related with Customer Promise, Scenarios and Deliverables.
Semester Planning
Every 6 months
Quarterly Planning
Every 3 months
Scenario Refinement
Ongoing
Sprint Backlog Refinement
Every sprint (1 month)
Sprint Planning
Every sprint (1 month)
Sprint Review & Retrospective
Every sprint (1 month)
J
A
S
O
N
D
J
F
M
A
M
J
J
A
S
O
N
D
J
F
M
A
M
J
J
A
S
O
N
D
J
F
M
A
M
J
J
A
S
O
N
D
J
F
M
A
M
J
J
A
S
O
N
D
J
F
M
A
M
J
J
A
S
O
N
D
J
F
M
A
M
J

## Slide 16
Overall Lifecycle
CPO
PO/EPO
CPO
PO/EPO
Capability Scenario Refinement
PO/EPO
PO/EPO
PO/EPO
Deliverable Refinement
Dev Team
Dev Team
Dev Team
Sprint Planning
Dev Team
Dev Team
Dev Team
Sprint Execution
Sprint Backlog
Sprint Backlog
Sprint Backlog
Customer
Promise
Quarterly Backlog
CapabilityScenario Backlog
CapabilityScenario Backlog
Deliverables
Deliverables
Deliverables
Customer Promise Refinement
CPO
Vertical Leads
PO/EPO
Dev Lead
Quarterly Planning
CPO
Vertical Leads
PO/EPO
Dev Lead

## Slide 17
Estimation
What | Who | How | Comments
Customer Promise | PO + Dev SME | T-shirt size | Existing t-shirt size
Scenario | Scrum team | Story points | 1 story point = 10 hours
Deliverables | Scrum team | Story points | 1 story point = 10 hours
Sprint tasks | Scrum team | Hours | 

## Slide 18
Sprint
Definition of Ready
Acceptance Criteria
Definition of Done

## Slide 19
Sprint Preparation
Definition of Ready Before a sprint starts, a product owner must ensure deliverables planned for the sprint meets DoR (Definition of Ready)
Deliverables are broken into small enough size to be delivered in a sprint
Sufficient documentation is done
Dev team has reviewed deliverables and all queries are clarified
Dependencies are identified and planned
Acceptance criteria is defined
Guidelines for Deliverables While there is no specific format for a deliverable, it should have sufficient information for dev team to understand the ask. Here are some of the guidelines for deliverable content.
Objective
Business value
Acceptance criteria
In-scope
Out-scope
Business rules
External dependency
UI wireframe (in any format) as applicable

## Slide 20
Sprint Planning
Acceptance Criteria
Acceptance criteria are defined by a PO for each deliverable
Related with validating implementation of business requirements
Must be tested as part of a sprint
Definition of Done
Definition of Done is related with exiting a sprint. It is defined at the org level and shall be common across all the teams.
Code is peer reviewed
Code is tested in SIT environment
All test bugs are closed
(As applicable) Ops guide is updated
(As applicable) Ops/SE training is completed
(As applicable) Release notes are updated
Test and deployment automation is completed
SOX dashboard is CLEAN

## Slide 21
Release
Cadence & Milestones
Scope Tracking
SOX Compliance

## Slide 22
 | Sprint 1 (4 weeks) |  |  | Sprint 2 (4 weeks) |  |  | Sprint 3 (4 weeks) | 
UAT 1 (2 weeks) |  |  |  | UAT 2 (2 weeks) |  |  | 
UAT 3 (2 weeks) |  |  | 
Each sprint to have 4 weeks for development and SIT testing
A follow up 2 weeks of UAT cycle to facilitate scenarios requiring formal UAT
All teams to follow the same release cadence
Crawl, Walk and Run
2 weeks of UAT cycle is built as a safety net as it will be too ambitious to include it in sprint to start with
In long term, 4 weeks of sprint shall include UAT and hence code can be deployed to production every 4 weeks.
Release Milestone | SOX Milestone
Sprint planning | Scope Lock
Sprint review | NA
SIT Sign off, Technical approval, GNG | Technical Approval, GNG
Go live | NA
Release Cadence & Milestones
There is no change in weekly release cadence or milestones

## Slide 23
Scope Tracking & SOX Compliance
Proposed Change
Instead of scenarios, we shall be tracking deliverables for release scope and SOX milestones
Now a scenario can span across releases (However as a best practice, don’t span it more than three releases)
As depicted below, a scenario can span multiple releases while associated deliverables can be deployed to production in intermediate releases
Why
Scenario is a logical piece of work which may need multiple production releases for completion
Current model does not support this as there must be a scenario for each release to production
SOX Compliance
All SOX controls remains as it is – Technical approval, UAT approval (on need basis) and GNG.
SOX does not force to use scenario for tracking.
OEM team is using deliverables for release scope and SOX milestones.
Scenario |  | 
1810 Release | 1811 Release | 1812 Release
D1 | D3 | D4
D2 |  | 

## Slide 24
What Next?

## Slide 25
Before We Start….
Have patience. A transformation takes its own time to operationalize
Churn is inevitable. Give a few release cycles for the process to fine tune and stabilize (OEM team took from more than six months!)
Understand and accept that every sprint may not have production code deployment
There won’t be any compromise on quality
Shift of mindset from waterfall to agile is essential

## Slide 26
Next Steps
What | Who | When
Finalize the Scrum process | LT + Core team | 
VSTS cleanup for existing work items | PMs + Dev leads | 
Setup necessary infrastructure (VSTS teams, area path clean up, dashboards etc.) | Dev leads | 
Create healthy backlog (Scenarios, deliverables) | PMs | 
Define capability development teams for Scrum | Dev leads | 
Finalize SE/SRE engagement model | LT + Core team | 
Train the entire team (PM, Dev, SE, SRE) | Core team | 
Rollout the process | Core team | 

## Slide 27
Appendix

## Slide 28
Proposed
Iteration : OSGS
Pending Assessment
Iteration : OSGS
Started
Pending Approval
Committed
Completed
Iteration : OSGS
Iteration : OSGS
Iteration : OSGS
Iteration : OSGS
State : Proposed
Tags : None
Owner : Vertical Lead
State : Proposed
Tags : VLAssessment
Owner : Capability PO / PO
State : Proposed
Tags : VLApproval
Owner : Vertical Lead
State : Committed
Tags : None
Owner : PO
State : Started
Tags : None
Owner : PO
State : Completed
Tags : None
Owner : PO
Customer Promise Lifecycle
Logical State | Description
Proposed | A new customer promise is created by a vertical lead
Pending Assessment | A customer promise is assigned to a capability PO for assessment
Pending Approval | Assessment is completed and a customer promise is pending for approval from vertical leads
Committed | A customer promise is approved for POR
Started | PO has started working on a customer promise (to create scenarios, deliverables etc.)
Completed | All work related to a customer promise is completed

## Slide 29
Customer Promise Backlog Refinement Cadence
What | When | Why | Who will own? | Who will Participate? | How? | Tracking
CP backlog Refinement | Every two weeks | To triage customer promises To assign a new CP to a capability PO for assessment To approve/reject CPs which have been assessed | Vertical Leads | Vertical Leads (Following as appropriate) Capability Product Owner Product Owner Dev leads | Skype meeting | VSTS dashboard

## Slide 30
New
Area Path : As appropriate
Started
Committed
Completed
Area Path : As appropriate
Area Path : As appropriate
Area Path : As appropriate
State : Proposed
Owner : PO
State : Completed
Owner : PO
Iteration : OSGS
Iteration : XXXX
State : Committed
Owner : PO
Iteration : As per release
State : Started
Owner : PO
Iteration : As per release
Scenario Lifecycle
Logical State | Description
New | A PO has created a new scenario for a customer promise
Committed | A scenario is planned for a particular release
Started | Team has started working on a scenario (associated deliverables are included in a sprint)
Completed | All work related to a scenario is completed

## Slide 31
Scenario & Deliverable Backlog Refinement Cadence
What | When | Why | Who will own? | Who will Participate? | How? | Tracking
Planning Increment | Every three months | To review scenarios planned for the next three releases (Note : This is a plan and not a firm commitment at this stage) | One of the senior PM (Rotation base) | All Vertical leads Capability Product Owner Product Owner(s) Dev Managers Scrum Master | In person + Skype | VSTS dashboard
Capability backlog refinement | Ongoing | To evaluate scenarios refined by Pos for details and business values To approve and prioritize scenarios for capability backlog | Capability Product Owner | Capability Product Owner Product Owner(s) Following is optional ScrumMaster | In person + Skype | VSTS dashboard
Sprint backlog refinement | One week before sprint start | To ensure deliverables have sufficient details for development team to include in a sprint planning | Product Owner | Product Owner ScrumMaster Development Team | In person + Skype | VSTS dashboard

## Slide 32
Sprint Ceremonies
What | When | Why | Who will own? | Who will Participate? | How? | Tracking
Sprint planning | First day of the sprint | To finalize scope for a sprint and task breakdown | Scrum Master | Scrum Team | In person | VSTS dashboard
Daily standup | Once in day during the sprint | To check progress What's done What's pending Any impediments | Scrum Master | Dev team Scrum Master PO is optional and will join on need basis | In person Dev team to reach out to Redmond PO as needed based on time zone feasibility | VSTS dashboard
Sprint review | At the end of the sprint | To review the outcome of a sprint for PO to decide to accept it or not | Scrum Master | Scrum team (As applicable) Ops/Business (Optional) CPO, Vertical leads | In person + Skype | NA
Retrospection | After the sprint | To learn and improve What went well What needs improvement | Scrum Master | Scrum Team | In person + Skype | One note

## Slide 33
Ceremonies
June
July
August
September
Semester Planning (CP)
Quarterly Planning
Sprint Backlog Refinement (Deliverables)
July Sprint – Review & Retrospective
July Sprint (Day 1) – Sprint Planning
Sprint Backlog Refinement (Deliverables)
Following example depicts timelines for different ceremonies related with Customer Promise, Scenarios and Deliverables.

## Slide 34
Well, some prep work will help

## Slide 35
MUST DO
Area path cleanup
Work item clean up (Customer Promise, Scenario, Deliverables)
  State
  Area path
Healthy capability backlog with prioritization
  Scenarios
  Deliverables
Creating VSTS teams for each Scrum team
Creating VSTS dashboards for sprint management

## Slide 36
OEM - Challenges
Mindset shift to deployable incremental scenarios/deliverables every month
  Assessment prior to Implementation
Prioritization across single backlog
  Long global PI planning meetings
  Time constraint vs Business value
Test (E2E/UAT) cycle is outside of sprint cycle
  2 week of UAT post sprint cycle causing churn in next sprint
Inconsistency in Scenario/Customer Promise documentation
  Open ended Vs MVP
Upstream/Downstream dependencies
  E2E testing window, schedule and test environments

## Slide 37
OEM - Benefits
Delivering incremental Business value sooner
  Faster time to Market
Easier to adjust scope to changing priorities
  Quarterly planning (PI) and Monthly Backlog Grooming
Building incremental features in shorter release cycles
  Business Ops integral part of team to provide early feedback
  High quality product to customers
Predictable Delivery
  Pretty good velocity
Overall and capability level Roadmaps
Simplified environment landscape with one release at a time

## Slide 38
OEM – Role Definition
Program Management
Customer Promise Owner
  CP definitions & prioritization
  Stakeholder Management
  Program Launch
  CP Roadmap
  E2E delivery
  Quantifiable business value
  Dependency Management
Capability PM Lead
  Capability Roadmap (incl. alignment to ‘Modern’)
  Scenario backlog prioritization
  Scenario definition/sequencing
  Upstream/Downstream dependency management
  Research, Design, Implement, Deliver
Capability PM
  Scenario definition/sequencing
  Upstream/Downstream dependency management
  Research, Design, Implement, Deliver
Customer Promise Refinement
CPO
Vertical Leads
PO/EPO
Dev Lead
CPO
Vertical Leads
PO/EPO
Dev Lead

## Slide 39
OEM - Capability Team with alignment to CPE Team
Team A
Team B
Team C
Team D
Customer Master
Agreement
AuthZ
Big Catalog
Price Composer
Fulfillment
Commercial Purchase
Billing
Capabilities
Capabilities
Capabilities
Capabilities
These are areas not regularly requiring new SAP features, so any new requirements will be handled via these teams
Team names TBD
SAP Capabilities
Billing
Revenue Recognition
SAP Capabilities
Big Catalog
Price Composer
Customer Master*
SAP Capabilities
Fulfillment
SAP Capabilities
Commercial Purchase (Order)
Agreement*
EC
SAP
Team E
Platform
Horizontal work e.g.- Platform Upgrade, AAD, UST Security etc.
Capabilities
SAP Capabilities
Platform
Horizontal work eg Security/Roles, SAP Technical Upgrades, Support Packs, etc

## Slide 40
OEM - Increment Planning Process
Scrum Master
Team Members
Team Product Owner
Scrum Master
Team Members
Team Product Owner
Scrum Master
Team Members
Team Product Owner
Build the plan to deliver working capabilities
Team Backlog
Team Backlog
Team Backlog
Program Increment Plan
Team PI Objectives
Team PI Objectives
Team PI Objectives
Alignment
Business Representatives
Chief Product Owner
Program Manager (PM)
Vision
Roadmap
Program Backlog
Program Customer Promises
Minimum Business Increment (MBI)