## Slide 1: OEMIT FY13 May Quarterly Release Kick-off Meeting
Alka Puri
OEMIT Release Leads
October 11, 2012

## Slide 2
Agenda
Team Roles and Responsibilities
Release Timeline
Project Candidates
Release Risks
Next Steps
Appendix
  Individual Projects
  SDLC Controls During Envision Phase (Pre-Baseline)

## Slide 3
Team Roles and Responsibilities
Solution Delivery Leads : Todd Nicholson (OEM Activation 3.0)
Jeff Yakubinis (All other FY13 MQR Programs)
Global OEM UAT Lead : Catherine Adams
Lead IT Program Manager : Feliks Shostak
Lead Development Manager : N J Wang
Lead SIT Test Manager : Rob Lynch
Release Program Manager : Alka Puri / Ramanujam Raghunathan
Release Engineering Lead : Mike Adams / Mahesh Chittaranjan
Release SIT Lead : Raghava Rao Sathuluri
Release SE Lead : Rohit Ratnakar Mallya
Production Support Manager : Tina Taylor
Release SMD Lead : Melissa Slichter/Jon Bloom
MQR Team Alias : FY13 May QR Team (mqr13tm)
MQR Release Owners Alias : FY13 May QR Owners (mqr13ro)

## Slide 4
FY13 MQR Timeline
OEM SIT using SAP MSU
SAP MSU Refresh – 02/15/2013 ; MST Refresh – 03/22/2013

## Slide 5
Area / Program | Project | Biz Owner | Architect | SM | PM | Project Level Kick-Off
FY13 MQR Key Projects |  |  |  |  |  | 
OA 3.0 | Win Next | Dermot McMahon | David Simler | Jason Shaw/Vineeta Singh | Tom Basham | TBD
OEM Data Simplification | OEM Data Simplification | Mark Gorski | Brian Shive | Jeff Yakubinis | Rudra D | TBD
OEM Non-Discretionary Other | OEM Platform Upgrade | N/A | N/A | Eric Burmester | Rajesh Narayanan | TBD
Embedded Business Growth | EDMP | Guillaume Estegassy | Shane Patton Sundeep Mahensaria [SMIT] | Shashi Lanka Venkata | Padma Yada Mohan Sai Krishna Allika [SMIT] | Oct 15
OA 3.0 | Embedded Onboarding | Dermot McMahon | David Simler | Rachel Bachmann | Padma Yada/ Cindi McCutchen | By 10/19
Quarterly Enhancements / Maintenance (MOO, DOC, ORION, OA3.0, SAP) |  |  |  |  |  | 
MOO-DOC-Orion | NBLB | Various |  | Clay Forsythe / Travis Wood | Srinivas Ponakampalli | TBD
SAP | SAP Enhancements | Various | Karthik Sikakollu | Eric Ristine | Michael Parpart | Dec 14th
OEM Tool Set | OEM Enhancements | Various | Shane Patton | Clay Forsythe | Mahua Chaudhri | Oct 15th potentially
Project Candidates

## Slide 6
Release Risks
Risk | Mitigation | Owner | Due Date
Availability of servers/hardware on time for build out of POC, DEV, DIT, SIT, UAT, HOF, PQ, PROD, DR based on upgraded OS (2012) platform | Team to continue working through it | Rajesh Narayan/Leadership team | 11/20/2012
Availability of adequate test resources to do regression testing | Test LT owns working through it; there may be additional funding request | Rob Lynch | 11/20/2012
Note: Full fledged Risk Assessment will be done during the Envision Phase

## Slide 7
Next Steps
Determine business, IT resource needs/commitments
Finalize and communicate schedule
Finalize resource assignments
Prepare FY13 MQR OEMIT SharePoint website
Determine external group impact (ITA, CorpSTS, FIT, SMIT, ICOE, PA, EDS, SAP, AVS)
Plan testing process/dates with SIT/UAT and SAP/ FeedStore leads
Create project entries in EAPM and Project Profiles in SDLTrack
Schedule Project Level Pre-Baseline meetings for completion by 11/20/2012
Start the journey toward Release Pre-Baseline

## Slide 8
Signers
For Release Kickoff, there are no designated signers. This is an informational meeting only.
With effect from Jan 1, 2010 as per ITLC guidelines published in Dec 2009, any Project > 500k need to conduct separate Project Kickoff meeting using new ITLC Project Kickoff deck template and collect approval signatures from Business, SD, Engineering and SMD.

## Slide 9: FY13 MQR Project Details

## Slide 10
OA 3.0 Win Next (placeholder)
Program Vision: OA 3.0 enhancements or new to support Win Next and Win 8
QR Objective
OA 3.0 New features/enhancements for Win Next and enhancements that are critical to run for OA 3.0
Key Performance Indicators
TBD – Will be determined when the scope is defined
Scope
This is a placeholder. Enhancements are being prioritized and Win Next assessment needs to happen to determine the scope.
Risks / Constraints / Dependencies
Risk – Delay in finalizing the scope can impact the delivery of the changes on time for Partners to onboard to OA 3.0 for Win Next.
Constraints – Win Next schedule (not yet know), Partners schedule.
Dependencies – Win Next assessment to determine changes required and scope
H2
H1
FY11
FY12
H2
FY13
H2
AQR
MQR
MQR
FQR
FQR
MQR
Capability Roadmap
MQR FY13
OA3.0 - Windows
H1

## Slide 11
OEMIT Non-Discretionary Other – Platform Upgrade
Program Vision: Align OEMIT Applications to First and Best and Stay Current Goals
Stay Current: Minimize risks to Apps/Services, and increase systems’ reliability by keeping them relevant (i.e. availability, performance, supportability, operability, security). In addition, help optimize Operations costs by minimizing the number of versions of retail software we manage in our MSIT Data Center, while making MSIT more relevant to MSFT through Showcase.
Provide new Technical infrastructure capabilities to implement OEM Business Roadmap required Features in future
QR Objective
Stay Current on Windows Server OS and SQL Server versions implemented on Pre-Production and Production servers hosting OEMIT Applications OA3.0, OSP, HAWK, MOO, DOC, Orion, LW, Datamart.
Contribute to FY13 CIO goals for Windows Server 2012 Adoption.
Key Performance Indicators
Ensure existing application functionality and performance are intact for OA3.0, OSP, HAWK, MOO, DOC, Orion, LW, Datamart
Meet/exceed FY13 CIO Target for Windows Server 2012 Adoption (15%)
Scope
All Web and App Servers (non-Database Servers) excluding SSRS Web Server
SQL Server Upgrade to SQL Server 2008 R2 SP2 on all Database Servers (minor inline upgrade)
Regression test from functional, user and performance perspectives the OEMIT applications OA3.0, OSP, HAWK, MOO, DOC, Orion, LW, Datamart.
Risks / Constraints / Dependencies
Risk – Availability of hardware and environments (POC, DEV, DIT, SIT, UAT, HOF, PQ, PROD, DR on time)
Constraints – Test resources and budget.
Dependencies – Completion of high priority Windows Server 2012 POC tasks in time to start formal MQR Platform Upgrade activities
H2
H1
FY11
FY12
H2
FY13
H2
AQR
MQR
MQR
FQR
FQR
MQR
Capability Roadmap
MQR FY13 -
Web, App Server 2012 Upgrade
H1
AQR FY14 -
Database Server 2012 Upgrade

## Slide 12
OEM Data Simplification
Program Vision: Streamline the processing and storage capacity of OEM environments that support OA/HAWK/MOO/DOC platforms to be
    Efficient in processing customer data without any redundant and/or unnecessary processing
    Optimized to leverage existing storage capacity
    Optimized to consolidate the master data
QR Objective
To enable us achieve the program vision, deliver on the following high priority objectives
Reduce data size by filtering
Consolidate dbs into same servers where there is minimal impact
Improve latency by using new feedstore acquisition options
Remove archived/unused data to improve supportability
Key Performance Indicators
Reduce Data size by approximately 1 TB per environment
Reduce Data latency for OEM specific data into COR
No negative impact to any OEM downstream system
Scope
Filtering of Feedstore data for OEM specific data
Consolidating of master data into a single hub using new feedstore acquisition option
Consolidate RPT databases into WHS server and DSS database into LICWiz server
Remove archived/unused data to improve supportability
Risks / Constraints / Dependencies
Risk – List of risks documented in VSTF under path OEMIT\Simplification
Constraints – Schedule constraint on code being complete for project scope items before release level Code Complete to align with env build out for DIT/SIT
Dependencies – EDS Feed store for new acquisition options and availability of filtered datasets
H2
H1
FY11
FY12
H2
FY13
H2
AQR
MQR
MQR
FQR
FQR
MQR
Capability Roadmap
MQR FY13
MOO/DOC
H1

## Slide 13
OEM Enhancements Project - Foundation
Program Vision: General improvements to OEM applications in support of usability, supply chain efficiencies, efficacy, and in support of Microsoft’s strategic agenda. - Support Microsoft’s strategic agenda for revenue control. - Increase efficiencies in supply chain, manufacturing, and general LOB applications for OEM. - Reduce support by Tier 2. - Improve end user experiences.
QR Objective
Enhancement work for Foundation Systems - MOO, DOC, Orion, Xbox & OSP
New pilot program related to VSTF full integration (TFS-SFE) will be utilized for one of the Enhancements proposed
Key Performance Indicators
The specific project benefits are tied to each individual OEMIT Enhancement. For MQR13, there is some cost savings, revenue generation, reduction in manual processes, some compliance material, and several CPE initiatives.
Proposed High Level Scope (to be locked at Baseline)
Supply Chain – Rule addition to RMA for EOL COA
Xbox – New contract supportability
CRMT – finance and SOX updates in Triangulation
Support – OSP Email, audit and automation changes
CRMT – Supplemental Invoice addition to DOC
CRMT – eAlerts updates, retirement of specific messages
CRMT – Sales Out Report modifications
CRMT – ODR Price List Tool restoration in DOC
CRMT – DOC update for Mappoint & CMT supportability
Risks / Constraints / Dependencies
To be identified and documented prior to the project kick-off on 10/15/2012
H2
H1
FY11
FY12
H2
FY13
H2
AQR
MQR
NQR
FQR
FQR
MQR
Capability Roadmap
H1

## Slide 14
Embedded Business Growth
Program Vision: EDMP will extend market reach by energizing and leveraging the Windows Embedded ecosystem to help grow Distributor business by driving new opportunities, encouraging business relationships between ecosystem partners and distributors, and building strategic partnership with Distributors that can deliver an end-to-end go to market solution to OEMs.
QR Objective
SAP: Improve Disti CPE
ESB: Improve Disti CPE & data accuracy
CRM: Improve Usability for Field Sales
CRM: Reduce manual workflow overrides and associated delays
Key Performance Indicators
Expanded OVRP benefits to breadth
Grow Breadth Revenue
Enhanced Pipeline Management
Reduced processing cost
Scope
SAP: Consolidated chargeback invoices
ESB: OVRP/CLA EDI
CRM: EDMP for Direct and MNA
CRM: Approval workflow improvements
CRM Outlook Client rollout
Risks / Constraints / Dependencies
Successful deployment of Chargeback calculations (FQR)
Availability of ESB resources to support implementation
H2
H1
FY11
FY12
H2
FY13
H2
AQR
MQR
NQR
FQR
FQR
MQR
Capability Roadmap
MQR FY13
EDMP Enhancements
H1
AQR
NQR
FQR
MQR

## Slide 15
OA 3.0 for Embedded
QR Objective
Onboard in-scope Embedded Direct OEMs to OA
Complete changes to support onboarding of Embedded FES & WES.
Complete all development and testing (including partner testing) in support of onboarding these OEMs.
Key Performance Indicators
TBD
Risks / Constraints / Dependencies
Risk – Customer engagement just started which could result in late requirements that we may not be able to accommodate.
Risk – Customer segmentation plan from FQR may result in data conversion needs in MQR, which could result in additional need for budget.
Dependencies – BG may leverage VAMT for bulk factory activations.
Scope
In scope items TBD out of Embedded gap analysis in FQR.
Scope items planned for official project kickoff.
H2
H1
FY11
FY12
H2
FY13
H2
AQR
MQR
NQR
FQR
FQR
MQR
Capability Roadmap
H1
Program Vision: Provide tools that will enable top volume Embedded OEMs to activate Window 8 FES in a high volume production environment.
The Embedded business is facing a significant challenge with the launch of their Windows 8 for Embedded Systems (Windows 8 FES) product. With Windows 8 FES, the BG will not be allowed to leverage Bypass (e.g., OA 2.1 used in Windows 7 FES) activation due to the significant piracy vector it would create for Windows 8 client. Therefore, the Embedded BG is limited to shipping Windows 8 FES using PKEA (product key entry activation) at launch, which will work for the majority of the small volume FES OEMs, but will be too cumbersome for their larger top volume OEMs. The Embedded BG is looking to implement OA 3.0 as a scalable solution for these top-volume OEMs to electronically purchase, receive and inject digital keys for their FES 8 shipments.

## Slide 16: Appendix

## Slide 17
SDLC Controls During Envisioning Phase (Pre-Baseline)
Provisioning
MSApps Entry
Complete Impact Assessment Questionnaire (ASAP via MSApps)
Role Segmentation for Data or Transaction Processing Access
Customer and Partner Profiling
Business requirements (define and sign-off)
Risk Assessment
Solution Assessment
Solution ROI
Business Case Analysis (BCA)
Independent Oversight Control
Project Vendor – Contract/PO
Pre-Baseline Meeting and signoff
Certain controls may or may not be applicable depending on SDLC Model a project falls
under (SDLC Full, Light, Ultra-light, Agile, and Hotfix).